## Purpose
Document Purpose:
- To provide a guideline for what activities should be performed by a Project Manager for both Projects and Programs
- To provide a sampling of what deliverables may be produced as a result of executing on that activity
- EPMO Required Output is expected as part of the FIS Enterprise Project Management Methodology (EPMM)
NOTE: Roles are not intended to equate to official HR job titles
This document contains confidential and proprietary information of Fidelity Information Services, LLC and/or its affiliates and subsidiaries (collectively “FIS”). In limited circumstances this document may be copied and/or distributed to an FIS client and its employees on a “need to know” basis in order to fulfill their responsibilities. Any further copying, reproduction, or distribution outside of FIS without express written consent is strictly prohibited. © 2015 FIS - All rights reserved worldwide
Activity Role Matrix
Template Version Number: 6.0
Last Revision Date: 12 December 2014

## RACI Definitions
Responsible
Those who do the work to achieve the task. There is typically one role with a participation type of responsible, although others can be delegated to assist in the work required.
Accountable
The one ultimately answerable for the correct and thorough completion of the deliverable or task, and the one from whom responsible is delegated the work. In other words, an accountable must sign off (approve) on work that responsible provides. There must be only one accountable specified for each task or deliverable.
Consulted
Those whose opinions are sought, typically subject matter experts; and with whom there is two-way communication.
Informed
Those who are kept up-to-date on progress, often only on completion of the task or deliverable; and with whom there is just one-way communication.
Very often the role that is accountable for a task or deliverable may also be responsible for completing it (indicated on the matrix by the task or deliverable having a role accountable for it, but no role responsible for its completion, i.e. it is implied). Outside of this exception, it is generally recommended that each role in the project or process for each task receive, at most, just one of the participation types. Where more than one participation type is shown, this generally implies that participation has not yet been fully resolved, which can impede the value of this technique in clarifying the participation of each role on each task.

## Project Activity Resp Matrix
WBS | Project Activity | Output | Project Manager | Project Analyst | Project Sponsor | Project Stakeholder | Customer Representative | Process Consultant/ EPMO | Business/ Conversion Analyst | Quality Assurance Analyst | Resource Manager | Sales Support Rep. | Team Lead | Team Member | Technical Lead | Solution Architecture | Training Coordinator
IP | Initiating and Planning Phase
IP.01 | Initiating Phase
| Register Project | Registered Project, Compliance Questionnaire (dev only), Project set up in Time Reporting System | A | I |  | I |  | C | I | I | I |  | I | I | I | I | I
IP.01.010 | Complete Sales/Organizational Turnover | Archived Sales/Organizational artifacts, Meeting Minutes | A | I | C | I |  |  | I |  |  | R | I |  |  | I | I
IP.01.020 | Initiate Planning Effort | Project document repository, Tracking Logs - Risk/Issues/Action Items/ Defects/Changes Planning Schedule, Client Introductory Meeting Minutes | A | I | C | C | C |  | C | C | I |  | C | I | C | C | C
| Required EPMO Output | Project Registration | A | I | I | I | I | C | I | I | I | I | I | I | I | I | I
|  | Compliance Questionnaire (dev only) | A |  | C |  |  | C | C
|  | Risk Tracking Tool | A | C | C | C | I |  | C | C | C |  | C | C | C | C | C
|  | Issue Tracking Tool | A | C | C | C | I |  | C | C | C |  | C | C | C | C | C
|  | Scope Change Control | A | C | C | C | I |  | C | C | C |  | C | C | C | C | C
IP.01 | Planning Phase
IP.01.030 | Establish Objectives | Project Definition: Objectives section | A | I | C | C | C |  | C | I | I | C | C | I | C | C | C
| Develop Requirements and Product Configuration Approach | Project Definition: High-Level Requirements section, Product Configuration | A |  | C | C | C |  | R | I |  |  | I | I | I | C | I
| Establish Initial Scope | Project Definition: Scope section | A | R | C | C | C |  | I | I |  |  | I | I | I | I | I
| Document Assumptions and Constraints | Project Definition: Assumptions and Constraints section | A | R | C | C | C |  | I | I |  |  | I | I | I | I | I
| Conduct Planning Kick-off Meeting - Client or Internal | Standard Kickoff Meeting presentation, Meeting Minutes capturing Action Items | A | C | C | C | I |  | C | C | C | I | C | I | C | C | C
IP.01.050 | Define Solution | Project Definition: Solution Overview section | A | C | C | C | C | C | C | C | I |  | R | I | R | R | C
IP.01.060 | Estimate Size and Effort | Project Definition: Size/Effort Estimates section Check Planned Implementation Date in EMS | A | R | C | C | I |  | C | C | I |  | C | C | C | C | C
IP.01.070 | Review Direction and Finalize Scope | Updated Project Definition: Objectives, Scope, Assumptions and Constraints, High-level Requirements sections | A | R | C | C | C |  | C | C | C | I | C | C | C | C | C
IP.02.010 | Create Work Breakdown Structure | Project Work Breakdown Structure | A | R | C | C | I | C | C | C | C |  | C | I | C | I | C
IP.02.040 | Perform Resource Planning | Training Plan, Project Definition: Project Team section | R | C | C | I | I |  | I | C | R |  | C | I | C | C | C
IP.02.050 | Create Schedule | Project Schedule | R | C | C | C | I |  | I | C | C |  | C | I | C | C | C
IP.02.060 | Prepare Budget | Project Budget | A: A; R: C; C: R; C: C |  | C |  | C
IP.02.070 | Perform Project Schedule Review | Approved Project Schedules, Project Definition: High Level Milestones section | A | I | R | R | R |  | R | C | R |  | R | C | R | C | R
| Required EPMO Output | Project Definition | A | C | C | C | I |  | C | C | C | I | C | I | C | C | C
|  | Communication Plan | A | C | C | C | I |  | C | C | C | I | C | I | C | C | C
|  | Kick-off Meeting | A | C | C | C | I |  | C | C | C | I | C | I | C | C | C
|  | Project Schedule | A | C | C | C | I |  | C | C | C | I | C | I | C | C | C
|  | Training Plan | A | C | C | C | I |  | C | C | C | I | C | I | C | C | R
IP.03 | Project Control Practices
IP.03.010 | Define Change Control Practice | Project Definition: Project Control Practices, Project Change Control section | A | C | C | C | C |  | C | I | C |  | C | I | C | I | C
IP.03.020 | Define Status Reporting Practice | Updated Project Status Report template, Project Definition: Updated Communication Management Practice (if applicable), Define Status Reporting Practices sections | A | I | I | C | C |  | I | C | I |  | R | I | R | I | C
IP.03.030 | Define Communication Management Practice | Project Definition: Communication Management Practice section, Communication Plan | R | I | C | C | C |  | I | I | C |  | I |  | I | I | I
IP.02.020 | Define Risk & Issue Management Practice | Project Definition: Risk and Issues Management Practice section, Risk/Issues Tracking Change Tracking (as applicable) | A | C | R | R | C |  | R | C | R |  | R | C | R | R | R
| Define Test & Acceptance Strategy | Project Definition: Project Control Practices, Test and Acceptance Strategy section OR Test and Acceptance Strategy template | A | C | C | C | C |  | C | R | C | I | C | I | C | C | C
| Define Configuration Management Activities | Project Definition: Configuration Management section | A | C | C | C | I |  | C | C | C | I | C | I | C | C | C
| Required EPMO Output | Status Report | A | C | C | C | I |  | C | C | C | I | C | I | C | C | C
|  | Communication Plan | A | C | C | C | I |  | C | C | C | I | C | I | C | C | C
|  | Risk Tracking Tool | A | C | C | C | I |  | C | C | C | I | C | I | C | C | C
|  | Issue Tracking Tool | A | C | C | C | I |  | C | C | C | I | C | I | C | C | C
|  | Test & Acceptance Strategy | A | C | C | C | I |  | C | C | C | I | C | I | C | C | C
|  | Updates to Project Definition artifact | A | C | C | C | I |  | R | R | C | I | C | I | C | C | C
IP.04 | Project Initiating and Planning Wrap-Up
IP.04.020 | Compile, Review, and Approve Project Definition | Approved Project Definition | A | I | R | R | C |  | R | C | R |  | R | I | R | R | R
IP.04.030 | Assess Initiating and Planning Phase | Initiating and Planning Lessons Learned Meeting Minutes | A | C | I | I |  | C |  | R | C |  | C |  | C | C | C
| Required EPMO Output | Updates to Project Definition artifact | A | C | C | C | I |  | R | R | C | I | C | I | C | C | C
EC | Executing and Controlling
EC.01 | Executing Phase
EC.01.010 | Conduct Project/Phase Kickoff Meeting | Project Kickoff Meeting presentation | A | I | C | I | C |  | C | I | C |  | C | I | C | C | C
| Manage Approvals | Approvals - Customer or Internal | A | C | I | I | C |  | C | C | I |  | C | C | C | C | C
| Required EPMO Output | Requirements Specification | A | I | C | C | C |  | R | I | I | C | I | I | I | C | I
|  | Functional Specification | A | I | I | I | C |  | R | I |  |  | I | I | I | C | I
|  | Technical Design Specification | A | I | I | I |  |  | C | I |  |  | C | I | R | C
|  | Product Definition | A | C | C | C | I |  | R | c | C | I | C | I | C | C | C
EC.01 | Lifecycle Specific
| Define Playbook Strategy | Playbook - Implementations | A | C | I | I | C |  | C | C |  |  | R | I | I | I | I
| Define Turnover Approach | Approved Turnover document, Handoff to Service Delivery, Action Plan for outstanding issues | A |  |  | C | I | bar: R to c; C; C to C
| Required EPMO Output | Playbook - Implementations | A | C | I | I | C |  | C | C |  |  | R | I | C | C | C
|  | Customer Facing Turnover | A | C | I | I | I | bar: R to c; C; C to C
EC.02 | Monitoring & Controlling
EC.03.010 | Update Project Management Artifacts | Updated Project Definition, Communication Plan, Training Plan, Requirements Specification, Test & Acceptance Strategy, Change Tracking, Project Budget, Project Schedule | A | R | C | C | bar: R to C; C to C
EC.02.020 | Manage Risks and Issues | Updated Risk/Issues Log | A | C | R | C | C | bar: R to C; C to C
| Monitor, Control and Report Project Performance | Updated Project Status Report, Updated Risk/Issues/Change Logs, Steering Committee Meeting Minutes | A | C | C | C | I | bar: R to C; C to C
EC.02.010 | Input Actual Implementation Date in EMS | Updated Date in EMS | A | C | C | C | I | bar: R to C; C to C
| Required EPMO Output | Status Report | A | C | C | C | I | bar: R to C; C to C
|  | Updated Project Schedule | A | C | C | C | I | bar: R to C; C to C
|  | Risk Tracking Tool | A | C | C | C | I | bar: R to C; C to C
|  | Issue Tracking Tool | A | C | C | C | I | bar: R to C; C to C
|  | Scope Change Control | A | C | C | C | I | bar: R to C; C to C
|  | Status Meeting Agenda | A | C | I | I | I | bar: R to c; C to C
|  | Meeting Minutes | A | I | I | I | I | bar: R to c; C to C
|  | Internal Steering Committee Meetings | A |  | C | C | C | bar: R; C to C
CL | Closing Phase
CL.02.010 | Collect and Analyze Project Data | Draft Project Closure Report: Executive Summary/Metrics, Change Control, Project related Issues, Project Processes, Follow-up items, Contract closure, and Archival Information sections | A | C | I | I | I | bar: R to C; C to C
CL.02.030 | Conduct Lessons Learned Meeting | Lessons Learned Meeting Minutes, Draft Project Closure Report: Lessons Learned section | A | C | C | C | C | bar: R to C; C to C
CL.02.040 | Prepare Project Closure Report | Approved Project Closure Report | A | R | bar: c
CL.03.010 | Archive Artifacts and Close Project | Closed Project, Updated Status in Time Tracking and Project Management Tools | A | R | bar: c
| Required EPMO Output | Customer Facing Turnover | A | R | I | I | C | bar: R to c; C; C
|  | Project Closure | A | R | I | I | C | bar: R to c; C to C
Note on I1: FIS: Combine
Note on J1: FIS: AI Look at if "Conversion Analyst" fits with BA (Susan)

## Program Activity Resp Matrix
Program Activity | Output | Program Manager | Project Manager | Project Analyst | Program Sponsor | Program Stakeholder | Customer Representative | Process Consultant/ EPMO | Resource Manager | Sales Support Rep. | Solution Architecture | Training Coordinator
Initiating and Planning Phase
Initiating Phase
Register Program | Registered Program, Compliance Questionnaire (dev only), Program set up in Time Reporting System | A | I | I | I | I |  | C | I |  | I | I
Complete Sales/Organizational Turnover | Archived Sales/Organizational artifacts, Meeting Minutes | A | R | I | C | I |  |  |  | R | I | I
Initiate Planning Effort | Program document repository, Tracking Logs - Risk/Issues/Action Items/ Defects/Changes Planning Schedule, Client Introductory Meeting Minutes | A | R | I | C | C | C |  | I |  | C | C
Required EPMO Output | Program Registration | A | I | I | I | I | I | C | I |  | I | I
| Compliance Questionnaire (dev only) | A | C |  | C |  |  | C
| Risk Tracking Tool | A | C | C | C | C | I |  | C |  | C | C
| Issue Tracking Tool | A | C | C | C | C | I |  | C |  | C | C
| Scope Change Control | A | C | C | C | C | I |  | C |  | C | C
Planning Phase
Establish Objectives | Program Definition: Objectives section | A | C | C | C | C | C |  |  | C | C | C
Develop Requirements and Product Configuration Approach | Program Definition: High-Level Requirements section, Product Configuration | A | C |  | C | C |  |  |  | C | C
Establish Initial Scope | Program Definition: Scope section | A | C |  |  | C | C |  |  |  | C
Document Assumptions and Constraints | Program Definition: Assumptions and Constraints section | A | C |  | C | C | C |  | C | C | C | C
Conduct Planning Kick-off Meeting - Client or Internal | Standard Kickoff Meeting presentation, Meeting Minutes capturing Action Items | A | R | C | C | C | I |  | C | I | C | C
Define Solution | Program Definition: Solution Overview section | A | R | C | C | C | C | C | I |  | R | C
Estimate Size and Effort | Program Definition: Size/Effort Estimates section Check Planned Implementation Date in EMS | A | R | I | C | C | I |  | R |  | R | C
Review Direction and Finalize Scope | Updated Program Definition: Objectives, Scope, Assumptions and Constraints, High-level Requirements sections | A | C | I | C | C | C |  | C | I | C | C
Create Work Breakdown Structure | Program Work Breakdown Structure | A | R | C | C | C | I | C | C |  | I | C
Perform Resource Planning | Training Plan, Program Definition: Program Team section | A | C |  | I | I | C |  | C |  |  | C
Create Schedule | Program Schedule | A | C | C | C | C | I |  | C |  | C | C
Prepare Budget | Program Budget | A | R | C | C |  |  |  | C
Perform Schedule Review(s) | Approved Program & Project Schedules, Program Definition: High Level Milestones section | A | R | I | R | R | R |  | R |  | C | R
Required EPMO Output | Program Definition | A | R | C | C | C | I |  | C | I | C | C
| Communication Plan | A | R | C | C | C | I |  | C | I | C | C
| Kick-off Meeting | A | R | C | C | C | I |  | C | I | C | C
| Program Schedule | A | R | C | C | C | I |  | C | I | C | C
| Training Plan | A | R | C | C | C | I |  | C | I | C | C
Program Control Practices
Define Change Control Practice | Program Definition: Program Control Practices, Program Change Control section | A | C | C | I | I | I |  | C |  | I | I
Define Status Reporting Practice | Updated Program Status Report template, Program Definition: Updated Communication Management Practice (if applicable), Define Status Reporting Practices sections | A | C | I | I | I | I |  | I |  | I | I
Define Communication Management Practice | Program Definition: Communication Management Practice section, Communication Plan | A | I | I | C | C | I |  | I |  | I | I
Define Risk & Issue Management Practice | Program Definition: Risk and Issues Management Practice section, Risk/Issues Tracking Change Tracking (as applicable) | A | C | I | C | C | I |  | I |  | I | I
Define Test & Acceptance Strategy | Program Definition: Program Control Practices, Test and Acceptance Strategy section OR Test and Acceptance Strategy template | A | C | I | I | I | I |  | I | I | I | I
Define Configuration Management Activities | Program Definition: Configuration Management section | A | C | I | I | C | C |  | I |  | C | I
Required EPMO Output | Status Report | A | R | I | I | I | I |  | I | I | I | I
| Communication Plan | A | R | I | I | I | I |  | I | I | I | I
| Risk Tracking Tool | A | C | C | C | C | I |  | C |  | C | C
| Issue Tracking Tool | A | C | C | C | C | I |  | C |  | C | C
| Test & Acceptance Strategy | A | R | C | C | C | I |  | C | I | C | C
| Updates to Program Definition artifact | A | R | C | C | C | I |  | C | I | C | C
Program Initiating and Planning Wrap-Up
Compile, Review, and Approve Program Definition | Approved Program Definition | A | R | I | I | I | C |  | I |  | I | I
Assess Initiating and Planning Phase | Initiating and Planning Lessons Learned Meeting Minutes | A | R | C | I | I |  | C | C |  | C | C
Required EPMO Output | Updates to Program Definition artifact | A | R | C | C | C | I |  | C | I | C | C
Executing and Controlling
Executing Phase
Conduct Program/Phase Kickoff Meeting | Program Kickoff Meeting presentation | A | R | I | C | I | C |  | C |  | C | C
Manage Approvals | Approvals - Customer or Internal | A | C | C | I | I | C |  | I |  | C | C
Required EPMO Output | Approvals - Customer and/or Internal | A | R | I | C | C | C |  | I | C | C | I
Lifecycle Specific
Define Playbook Strategy | Playbook - Implementations | A | R | I | I | I | C |  | I |  | C | I
Define Turnover Approach | Approved Turnover document, Handoff to Service Delivery, Action Plan for outstanding issues | A: A; R: C; C: C; I: I |  |  | I
Required EPMO Output | Playbook - Implementations | A | R | I | I | I | C |  | I |  | C | I
| Customer Facing Turnover | A | C | C | I | I | C
Monitoring & Controlling
Update Program Management Artifacts Lifecycle Artifacts | Updated Program Definition, Communication Plan, Training Plan, Requirements Specification, Test & Acceptance Strategy, Change Tracking, Program Budget, Program Schedule | A | R | C | C | C |  |  | C |  | I | I
Manage Risks and Issues | Updated Risk/Issues Log | A | R | C | C | C | C |  | C |  | C | C
Input Actual Implementation Date in EMS | Updated Date in EMS | A | R | C | C | C | I |  | C |  | I | C
Monitor, Control and Report Program Performance | Updated Program Status Report, Updated Risk/Issues/Change Logs, Steering Committee Meeting Minutes | A | R | C | C | C | I |  | C |  | I | C
Required EPMO Output | Status Report | A | C | C | C | C | I |  | C |  | C | C
| Updated Program Schedule | A | C | C | C | C | I |  | C |  | C | C
| Risk Tracking Tool | A | C | C | C | C | I |  | C |  | C | C
| Issue Tracking tool | A | C | C | C | C | I |  | C |  | C | C
| Scope Change Control | A | C | C | C | C | I |  | C |  | C | C
| Status Meeting Agenda | A | C | C | I | I | I |  |  |  | C | C
| Meeting Minutes | [9 empty] | I | I | bar: A to I
| Internal Steering Committee Meeting | [9 empty] | C | C | bar: A to I
Closing Phase
Collect and Analyze Program Data | Draft Program Closure Report: Executive Summary/Metrics, Change Control, Program related Issues, Program Processes, Follow-up items, Contract closure, and Archival Information sections | A | C | C | I | I | I |  | C |  | I | C
Conduct Lessons Learned Meeting | Lessons Learned Meeting Minutes, Draft Program Closure Report: Lessons Learned section | [9 empty] | I | C | bar: A to I; C
Prepare Program Closure Report | Approved Program Closure Report | A: A; R: C; C: R
Archive Artifacts and Close Program | Closed Program, Updated Status in Time Tracking and Project Management Tools | bar: A to C
Required EPMO Output | Program Closure | A | C | C | I | I | C |  |  |  | C | C